TOGETHER, International Network of Territories of Co-responsibility – 2014 Action Plan Calendar

General objective : Making Together network a strength for development of the co-responsibility for the well-being of all, within and between civil society and public authorities

| Axis | Kind of activities | 1er quarter : Consolidation phase | 2eme quarter : Skills extension phase | 3eme quarter : Proposals phase | 4eme quarter : Dialogue phase |
| --- | --- | --- | --- | --- | --- |
| 1- Basic Functions | Resources Centre | - Installation of the physical centre in the headquarters | - Sharing the resources in the WEB |  |  |
|  | WEBsite | - Making the site WEB attractive for all kinds of public - Evolution toward wiki | - Enlargement of SPIRAL community to independent groups of citizens |  |  |
|  | Methodology improvements a) Territories | - Introduction of wiki in co-construction of methodology spiral (from spiral to wikispiral) | - Progressive and flexible consolidation of wikispiral | - Proposal of large methodological scheme, linking different approaches | - Meeting in France about SPIRAL and Agenda 21 (inviting CittaSlow) |
|  | Methodology Improvements b) Collective actors | - Formalization of the methodological framework for collective actors, starting from the existing experiences | - Spreading in enterprises schools, hospitals, ,… | - Constitution of networks of co-responsibility in collective actors | - Meeting about wikispiral in collective actors |
|  | Research & Development | - Finalization of the semantic codification of the criteria and elaboration of the indicators of progress in well-being at different levels (from local to global) - Introduction of wiki in the participative co-evaluations | - Depth statistic-semantic analysis of the data base of criteria of well-being - Development of the participative co-evaluations and of the 3rd cycle of Spiral | - Proposals emerging from the results of the statistic-semantic analysis of the data base of the criteria of well-being and respective indicators. | - Meeting(s) during the 4eme quarter about public policies for the development of co-responsibility for the well-being of all. The number (one or several decentralized) the places (jointly with the meeting in France about agenda 21 and SPIRAL, and/or Strasbourg, and/or Brussels, and/or where the caravan of the co-responsibility finished, if different,…) will be decided during the year, depending on the evolution of the different activities and taking into account the preparation of the 3rd International meeting in Braine-l’Alleud in 2015. One of them will be the Seminar about policies for a participative and integrated management of common goods |
|  | Training/follow up | - Finalizing on line the tools for every king of training - Clarifying/reinforcing the network of SPIRAL dynamisors | - Training of the dynamisors and trainings in general for using the new available tools, namely the one for participative co-evaluations and 3rd cycle of spiral steps. |  |  |
| 2- Exchanges and solidarity between territories | Fund to support co-responsibility projects | - Definition of the procedures and installation of the Fund - First experimental projects and fundraisings | - Communication inside and outside Together network | - Elaboration of political proposals form the experience of the fund |  |
|  | Thematic networks a) Capacity building | a) From 12/2013 for every of the 12 thematic networks : - Collecting the existing experiences around the theme, inviting them to participate in the thematic network; - Developing one or different reference model(s) that are flexible and can be adapted to different contexts, enhancing principles and success factors; - Identifying possible new pilot activities that would be necessary to further develop the model(s); - Defining the forms of support, training to actors showing interest to develop this theme in their territories. | - Participative co-evaluations per action and kind of actions in every thematic network - Global synthesis | Elaboration of proposals in every thematic network, based on : - the results of the participative co-evaluations - the drawn lessons of the pilot experimentations |  |
|  | Thematic networks b) Transfers and pilot activities | b) From February - First transfers/supports from territory to territory - Launching the identified pilot activities | - Continuation of the actions of transfer - Continuation of the pilot activities - Drawing the lessons from the pilot activities |  |  |
| 3- Public policies | Role of publics authorities for developing co-responsibility | - Preparation of the conceptual framework | - Seminary of preparation of the trainings | - Seminars/trainings in different countries and for different target groups |  |
|  | NOW-BE-ALL project | - Communication about the project and invitation to participate in it | - Seminary for analysis of the proposals and launching of the groups by theme | - Elaboration of proposals in every group |  |
| 4- Promotion | Caravan of the co-responsibility | - Experimental launching of the caravan of the Co-responsibility in Romania |  | - Extension of the caravan at European (or global, including Africa) level |  |
|  | Virtual spaces (Facebook, Tw) | - Launching and animation |  |  |  |
|  | Leaflets/publications |  |  |  |  |
| 5- Part-nerships | Partnership with CittaSlow | - Formalizing the collaboration from results of 2013 training | - Common trainings, following the one in Italy (Novellara may 2013), to be organized in other countries |  |  |
|  | Others (to be completed) |  |  |  |  |